## 2025 (hidden)
Task/Activity | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | WJT | LYT | ZGH | WXG | CK
The 2nd Benchmarks | 115 | - | 165 | - | 60 | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y | Y | Y | Y
TSN Network Applications (standards needed) |  | - | - | - | - | - | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y | Y
C.1. Assembly of network demo examples from SDK and running on simulator (2 instances) |  | - | - | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y |  | Y
C.2. Porting and support of TSN for FreeRTOS from the FreeRTOS-Plus-TCP package | - | - | - | - | - | - | - | - | - | - | + | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
D. NXP LS1028A Reference Design Board and the Dragonfly DB Test Stand | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y | Y | Y
D.1. Powering up the LS1028ARDB, booting, kernel compilation, firmware flashing, starting the debugger, etc. | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  | Y
D.2. Demo example of CAN communication between LS1028ARDB and Dragonfly DB. A demo example with functionality identical to the can-utils package (for Linux). | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  | Y
D.3. Demo example of TSN communication between LS1028ARDB and Dragonfly DB (without redundancy). Performance measurement | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
D.4. Demo example of TSN communication between LS1028ARDB and Dragonfly DB with 802.1cb redundancy. Performance measurement. | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
D.5. Interactive program for working with network protocols, redundancy protocols, and partial packet control functionality based on the DragonFly DB board and the Fish demo program. | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
E. TI TMDX654IDKEVM Reference Design Board and the Dragonfly DB Test Stand | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y | Y | Y
E.1. Powering up the board, booting, kernel compilation, firmware flashing, starting the debugger, etc. Creating documentation on the sequence of actions and possible configuration parameters. | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  | Y
E.2. Demo example of CAN communication between TMDX654IDKEVM and Dragonfly DB. A demo example with functionality identical to the can-utils package (for Linux). | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y | Y
E.3. Demo example of TSN communication between TMDX654IDKEVM and Dragonfly DB (without redundancy). Performance measurement | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
E.4. Demo example of TSN communication between TMDX654IDKEVM and Dragonfly DB with 802.1cb redundancy. Performance measurement. | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
F. Create Eclipse-based IDE | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y | Y
H. TK2 Demo Development for Industry Events and Exhibitions | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
G. TK1 (X4) Competitor Analysis and Benchmarking | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y | Y | Y
[TK1][Bencmarks]Rv64sim in TK1 SDK | [25 empty] | Y | Y | Y
[TK1][Hi3093][Bencmarks]Bencmarks test | [27 empty] | Y
[TK1][RK1808][Bencmarks]Bencmarks test
[DFLY] [SDK][1.2.3] Test taike-1.2.3 sdk | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
[DFLY] [SDK][1.2.4] Test taike-1.2.4 sdk | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y | Y | Y
[DFLY][SDK][1.2.4] DFLY SDK v1.2.4 Long term Test Cases | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y | Y
| - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
| - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -

## lyt
Task/Activity | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | WJT | LYT | ZGH | WXG
The 2nd Benchmarks | + | + | + | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y
TSN Network Applications (standards needed) | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y
C.1. Assembly of network demo examples from SDK and running on simulator (2 instances) | - | - | - | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y
C.2. Porting and support of TSN for FreeRTOS from the FreeRTOS-Plus-TCP package | - | - | - | - | - | + | - | - | - | - | + | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y
D. NXP LS1028A Reference Design Board and the Dragonfly DB Test Stand | - | - | - | - | - | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y
D.1. Powering up the LS1028ARDB, booting, kernel compilation, firmware flashing, starting the debugger, etc. | - | - | - | - | - | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y
D.2. Demo example of CAN communication between LS1028ARDB and Dragonfly DB. A demo example with functionality identical to the can-utils package (for Linux). | - | - | - | - | - | - | + | - | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y
D.3. Demo example of TSN communication between LS1028ARDB and Dragonfly DB (without redundancy). Performance measurement | - | - | - | - | - | - | - | - | + | - | + | - | + | - | - | - | - | - | - | - | - | - | - | - |  | Y
D.4. Demo example of TSN communication between LS1028ARDB and Dragonfly DB with 802.1cb redundancy. Performance measurement. | - | - | - | - | - | - | - | - | - | + | + | - | + | - | - | - | - | - | - | - | - | - | - | - |  | Y
D.5. Interactive program for working with network protocols, redundancy protocols, and partial packet control functionality based on the DragonFly DB board and the Fish demo program. | - | - | - | - | - | - | + | - | + | - | + | - | + | - | + | - | - | - | - | - | - | - | - | - |  | Y
E. TI TMDX654IDKEVM Reference Design Board and the Dragonfly DB Test Stand | - | - | - | - | - | - | - | - | + | - | - | + | + | - | - | - | - | - | - | - | - | - | - | - |  | Y
E.1. Powering up the board, booting, kernel compilation, firmware flashing, starting the debugger, etc. Creating documentation on the sequence of actions and possible configuration parameters. | - | - | - | - | - | - | - | - | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y
E.2. Demo example of CAN communication between TMDX654IDKEVM and Dragonfly DB. A demo example with functionality identical to the can-utils package (for Linux). | - | - | - | - | - | - | - | - | - | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y
E.3. Demo example of TSN communication between TMDX654IDKEVM and Dragonfly DB (without redundancy). Performance measurement | - | - | - | - | - | - | - | - | - | - | - | + | + | - | - | - | - | - | - | - | - | - | - | - |  | Y
E.4. Demo example of TSN communication between TMDX654IDKEVM and Dragonfly DB with 802.1cb redundancy. Performance measurement. | - | - | - | - | - | - | - | - | + | - | - | + | + | - | - | - | - | - | - | - | - | - | - | - |  | Y
The Second Round of Benchmarks | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | - | - | - | - | - | - | - | - | - |  | Y
F. Create Eclipse-based IDE | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | - | - | - | - | - | - | - |  | Y
H. TK2 Demo Development for Industry Events and Exhibitions | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | - | + | - | - | - |  | Y
G. TK1 (X4) Competitor Analysis and Benchmarking | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | - | - | - |  | Y
[TK1][Bencmarks] TK1 SDK | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | - |  | Y
[DFLY] [SDK][1.2.3] Test taike-1.2.3 sdk | - | - | - | - | - | - | - | - | - | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - |  | Y
[DFLY] [SDK][1.2.4] Test taike-1.2.4 sdk | - | - | - | - | - | - | - | - | - | - | - | + | - | + | + | - | - | - | - | - | - | - | - | - |  | Y
[DFLY][SDK][1.2.4] DFLY SDK v1.2.4 Long term Test Cases | - | - | - | - | - | - | - | - | - | - | - | + | - | + | + | - | - | - | - | - | - | - | - | - |  | Y
Gerrit Server and Codes Review | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | - | + | + | + | + | - | - |  | Y
Two China Electronic Exhibitions | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | - | - |  | Y

## wxg
Task/Activity | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | WJT | LYT | ZGH | WXG | CK
Develop and test the CAN driver for the DFLY development board on the Zephyr operating system. | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  | Y
Read and study the benchmark code | - | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  | Y
Benchmark tests were performed on the HPM6E00 and SAM71Q21 development boards, and a report was compiled. | - | - | + | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  | Y
Integrating and refactoring the HPM6E00 and SAM71Q21 benchmark test code | - | - | - | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  | Y
Learn the yocto compilation system and use yocto to compile the LS1028ARDB development board image. | - | - | - | - | - | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  | Y
Set up the hardware environment and test the CAN communication between the LS1028ARDB development board and the DFLY development board. | - | - | - | - | - | - | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  | Y
Learn and read the CANUtils program code for Linux, and port it to the DFLY development board. | - | - | - | - | - | - | - | + | + | - | + | + | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  | Y
Use yocto to compile the TMDX654IDKEVM development board image file and test its CAN communication function. | - | - | - | - | - | - | - | - | - | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  | Y
Set up the hardware environment, test the CAN communication between DFLY and the LS1028ARDB and TMDX654IDKEVM development boards, and analyze any problems that arise. | - | - | - | - | - | - | - | - | - | - | + | + | - | - | - | - | - | - | - | - | - | - | - | - |  |  |  | Y
Port the benchmark program to competing development boards, test them, and compile a report. Competing development boards include: AT32F437ZMT7, GD32F470Z, GD32G553Rx, APM32F407IGT6, AC78406YGLA, Hisilicon 3065H, and WCH CH32V307V-EVT-R2. | - | - | - | - | - | - | - | - | - | - | - | - | + | + | + | + | - | - | - | - | - | - | - | - |  |  |  | Y
Port the CANUtils program to competing development boards and test CAN communication with the DFLY development board. Competing development boards include: AC78406, gd32g553, AT32F437, gd32f470z, and ch32v307v. | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | + | - | - | - | - | - | - |  |  |  | Y
Learn the chip architecture of Cortex M3/M4 and RISC-V and the key points of RTOS porting, and write code to test them. | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | - | + | - | - | - |  |  |  | Y
Learn and test several servos; write programs to control the servos using the DFLY development board. | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | - | - | - | - |  |  |  | Y
Learn and test the TK1 SDK, and read the u-boot and openSBI code. | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | - | - | - |  |  |  | Y
Compile the HI3093 development board image; port several programs such as Dhrystone, Whetstone, Coremark-PRO, and lmbench to the HI3093 development board and perform benchmark tests. | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | - | - |  |  |  | Y
| - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -

## zgh
Task/Activity | January |  | February |  | Marc |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | WJT | LYT | ZG | WXG | CK
[DFLY] [FreeRTOS] DFLY TDM Wiring Issues | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
[DFLY][FREERTOS] ow to compile GPIODemo wit soft floating-point | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
[DFLY] [TSNCmdDemo] Test Issue | - | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
[DFLY] [Bencmarks] Test tuning | - | - | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
[DFLY] [SDK] Unable to connect to openocd server using gdb tool in taike sdk | - | - | - | - | - | - | - | - | - | - | - | + | - | - | - | - | - | + | - | - | - | - | - | - |  |  | Y
[DFLY] [SDK] Compiling zepyr samples | - | - | - | - | - | - | - | - | - | - | - | + | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
[DFLY][SDK]Learn and write Demo of DFLY TSN 8021.CB | - | - | - | - | - | - | - | - | + | + | + | + | + | - | - | + | - | - | + | + | - | - | - | - |  |  | Y
[DFLY][SDK][1.2.4] Learn and test DFLY 1.2.4 sdk Demo about TSN | - | - | - | - | - | - | - | - | - | - | - | - | + | + | + | + | - | - | - | - | - | - | - | - |  |  | Y
[DFLY] [SDK][1.2.3] Test taike-1.2.3 sdk | - | - | - | - | - | - | - | - | - | + | + | - | + | + | - | - | - | - | - | - | - | - | - | - |  |  | Y
[DFLY][SDK][1.2.2] LwIPDemo cannot enter te Fis command line wen running on te rv2sim simulator, but it works wen downloaded to te DFLY development board | - | - | + | + | - | + | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
[PC][TSN]Use an external industrial network card i225 on a PC（QXG-2G4T-I225） | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | - | - | - | - | - | - | - | - | - |  |  | Y
[DFLY] [SDK] Fixed te issue tat taike sdk printf cannot print floating point data | - | - | - | - | - | - | - | - | - | + | - | - | - | - | - | + | - | - | - | - | - | - | - | - |  |  | Y
[PM6E00EVK][TSN]Test official use cases of TSN | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | - | - | - | - | - | - | - | - | - |  |  | Y
[DFLY][SDK][1.2.4] DFLY SDK v1.2.4 Long term Test Cases | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | - | - | - | - | - | - | - | - |  |  | Y
[DFLY][SDK]Create Eclipse-based IDE | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | + | + | - | - | - | - | - |  |  | Y
[DFLY] [SDK] [GDB] After executing monitor reset ，DFLY.cpu0 DFLY.s40 tap-disable | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | - | - | - | - | - | - |  |  | Y
[DFLY] [SDK-1.2.4] [FLAS] Tere is a problem wit erasing te flas in a certain scenario. | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | - | - | - | - | - | - | - |  |  | Y
[DFLY][TSN]Network performance test of eac development board (result visualization) | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | - | - | - |  |  | Y
[TK1][SDK][1.1.12] RV64SIM simulation operation tk1-smode.cfg | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | - | - | - |  |  | Y
[TK1][SDK][1.1.12] Compile bencmarks, and use rv64sim to simulate execution failure | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | - | - |  |  | Y
[TK1][Bencmarks]Rv64sim in TK1 SDK | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | - | - |  |  | Y
[TK1][SDK][1.1.12] Simulate running te uboot, kernel,rootfs of TK1 on te Qemu platform | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | - | - | - |  |  | Y
[DFLY] [SDK] ow to burn a new drboot.bin | - | - | - | - | - | - | - | - | - | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
[DFLY] Organize Bencmarks Test Result | + | + | + | + | + | - | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
[Boards] [Linux] Port Bencmarks | + | + | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
[DFLY][SDK]Porting and Support of TSN for FreeRTOS wit FreeRTOS-Plus-TCP | - | - | - | - | + | + | + | + | + | + | + | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | Y
[DFLY][TSN]Summary TSN test results into a file | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | + | - | - | - | - | - | - | - | - |  |  | Y
[DFLY][SDK]Demo Example of TSN Communication | - | - | - | - | - | + | - | + | - | - | - | + | + | + | - | - | - | - | + | - | - | - | - | - |  |  | Y
[TK1][RK1808][Bencmarks]Bencmarks test | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | + | + | + | - |  |  | Y